## RAID
R A I D L O G
ID | Description | RAID Category | Date identified | Status | Impact | Task ref. | Action required | Priority | Owner | Due date | Notes
R01 | An increase in licensing costs | Risk | 14/05 | Under Review | Potential project budget overrun | TSK_01 | Verify impact on the project budget
A01 | Lead developer will be available from 1 July. | Assumption | 17/05 | Confirmed | Project timeline | TSK_02 | Adjust project timeline
I01 | Server down | Issue | 20/06 | Unresolved | Dev team cannot complete their tasks | TSK_03 | Provide an update when the issue is likely to be resolved.
D01 | Third-party integration will take 3 weeks | Dependency | 23/06 | Todo | Project timeline | TSK_04 | Confirm duration of 3rd party integration with the vendor

## Data
Categories
Risk
Issue
Assumption
Dependency