## Backlog
Effort
Item ID | Type | Product Backlog Item | Notes | Priority | Dependencies | Story Points | Planned Sprint #
ID_01 | User story | User Login | This is a fundamental feature required for any user interaction with the application. It must be implemented first as it serves as the basis for other functionalities. | High | None | 8
ID_02 | User story | Profile Management | Users need to manage their profiles after logging in | High | User Login | 13
ID_03 | User story | Payment Integration | Payment is a critical feature that should be completed early but requires users to be able to log in first. | High | User Login | 21
ID_04 | User story | Order Tracking | Tracking orders is essential once payment integration is complete | High | Payment Integration | 5
ID_05 | User story | Notifications | Notifications enhance user engagement and rely on user profiles and login functionality. | Medium | User Login, Profile Management | 8
ID_06 | User story | Reporting | Reporting is crucial for tracking and analyzing data, which depends on order tracking. | Medium | Order Tracking | 13
ID_07 | User story | Dashboard | The dashboard provides a comprehensive view of the data and requires reporting to be in place. | Medium | Reporting, Profile Management | 21
ID_08 | User story | Search Functionality | Search functionality improves user experience | Medium | None | 8
ID_09 | User story | User Settings | User settings allow customization and require user profile management and login. | Medium | User Login, Profile Management | 5
ID_10 | User story | Data Export | Data export functionality depends on the reporting feature to provide the data to be exported. | Low | Reporting | 5
ID_11 | User story | Chat Support | Chat support enhances user support and requires user login. | Low | User Login | 13
ID_12 | User story | Analytics Integration | Analytics integration depends on the reporting feature to provide data for analysis. | Low | Reporting | 5
ID_13 | Task | Other | Reset PW to Dev enviroment | High | none | 1
ID_14 | Bug | User Login button | User login screen button is the wrong color | High | none | 2
|  |  | Total Story points |  |  | 128
Aproximate number of sprints required to complete the project

## Team capacity
|  |  |  | Total capacity |  | Sprint | Story Points Completed
Name | Role | Availability | Meetings | Hrs. | Story points | Sprint 1 | 20
Sarah | Developer |  |  |  |  | Sprint 2 | 25
John | Developer |  |  |  |  | Sprint 3 | 22
Mike | Developer |  |  |  |  | Sprint 4 | 30
Emily | Tester |  |  |  |  | Sprint 5 | 28
Total capacity in hrs |  |  |  | 0 | 0 | Average Sprint Velocity | 0
Estimated Sprint 6 team capacity |  |  |  |  | 0

## Sprint 6
task ID | Item type | Item | Description | Priority | Dependencies | Estimated Effort (story points)
Total story points