## Product Backlog
Item ID | Product Backlog Item | Notes | Priority | Dependencies | Story Points | Sprint
ID_01 | User Login | This is a fundamental feature required for any user interaction with the application. It must be implemented first as it serves as the basis for other functionalities. | High | None | 8
ID_02 | Profile Management | Users need to manage their profiles after logging in | High | User Login | 13
ID_03 | Payment Integration | Payment is a critical feature that should be completed early but requires users to be able to log in first. | High | User Login | 21
ID_04 | Order Tracking | Tracking orders is essential once payment integration is complete | High | Payment Integration | 5
ID_05 | Notifications | Notifications enhance user engagement and rely on user profiles and login functionality. | Medium | User Login, Profile Management | 8
ID_06 | Reporting | Reporting is crucial for tracking and analyzing data, which depends on order tracking. | Medium | Order Tracking | 13
ID_07 | Dashboard | The dashboard provides a comprehensive view of the data and requires reporting to be in place. | Medium | Reporting, Profile Management | 21
ID_08 | Search Functionality | Search functionality improves user experience | Medium | None | 8
ID_09 | User Settings | User settings allow customization and require user profile management and login. | Medium | User Login, Profile Management | 5
ID_10 | Data Export | Data export functionality depends on the reporting feature to provide the data to be exported. | Low | Reporting | 5
ID_11 | Chat Support | Chat support enhances user support and requires user login. | Low | User Login | 13
ID_12 | Analytics Integration | Analytics integration depends on the reporting feature to provide data for analysis. | Low | Reporting | 5
Total Story points
Aproximate number of sprints required to complete the project

## Sprint Outcomes
Sprint | Story Points Completed
Sprint 1 | 20
Sprint 2 | 25
Sprint 3 | 22
Sprint 4 | 30
Sprint 5 | 28
Average Sprint Velocity